JobLink Hub

Team Work Breakdown Plan

4 Members  |  2 Backend  ·  2 Frontend  |  7 Weeks

# 1. Team Overview

JobLink Hub will be built by a team of four developers split evenly between backend and frontend responsibilities. Each developer owns a clearly defined domain so work can happen in parallel without blocking each other.

Backend Dev 1 (BE1) — Database Design, Core API & Opportunity Module

Backend Dev 2 (BE2) — Authentication, Services Layer & Notifications

Frontend Dev 1 (FE1) — Public-Facing Pages, Job Search & Candidate Profiles

Frontend Dev 2 (FE2) — Dashboards, Shared UI Components & Admin Panel

# 2. Individual Responsibilities

## Backend Dev 1 — Database, Core API & Opportunities

BE1 owns the foundation that the entire project builds on — the database schema and the Opportunities (Jobs) module.

- Design and set up the full database schema (Users, Profiles, Opportunities, Applications, Skills, Notifications)

- Write and manage all Entity Framework Core migrations

- Seed the database with test categories, skills, and sample data

- Build the AppDbContext and all repository classes

- Implement all Opportunity API endpoints: list, filter, search, create, update, delete, view tracking

- Implement the Applications API endpoints: submit, view, withdraw, status updates

- Implement the Saved Jobs / Saved Opportunities endpoints

- Implement the Skills and Categories lookup endpoints

- Write unit and integration tests for the above modules

- Write and maintain Swagger/OpenAPI documentation for all endpoints

## Backend Dev 2 — Authentication, Services & Notifications

BE2 handles all security, business logic services, and the notification pipeline that the frontend and BE1 depend on.

- Set up ASP.NET Identity with role-based access control (Job Seeker, Employer, Admin)

- Build the full auth flow: register, login, logout, email verification, password reset

- Implement JWT token generation, validation, and refresh token mechanism

- Build the User Profile service (candidate and employer profile CRUD)

- Build the Application service (business rules for applying, status transitions)

- Build the Recommendation / Matching service (opportunity matching by skills)

- Build the Notification service and email templates (SendGrid / SMTP)

- Set up Hangfire background jobs for scheduled emails and alerts

- Build the Dashboard API endpoints (stats for candidate, employer, admin)

- Write unit tests for all services and auth flows

## Frontend Dev 1 — Public Pages & Job Search

FE1 builds everything a visitor or job seeker sees before and during their job search — the public-facing experience of the platform.

- Set up the Razor Pages project structure, shared layout, header, footer, and navigation

- Build the Home page: featured opportunities, platform stats, call-to-action sections

- Build the Opportunities Listing page: paginated cards, keyword search bar, filter panel

- Build the Opportunity Detail page: full description, employer info, apply button, save button

- Build the Candidate Browse page: searchable candidate cards with skills and location

- Build the Candidate Profile Detail page: bio, skills, education, experience, resume download

- Build the Employer Browse page: company cards with open positions count

- Build the Employer Profile Detail page: company info, active listings

- Build the Login and Registration pages with client-side validation

- Build the Blog listing and Blog detail pages

- Build the Contact and Pricing pages

- Ensure all public pages are fully mobile-responsive using TailwindCSS

## Frontend Dev 2 — Dashboards, Components & Admin Panel

FE2 builds the authenticated experience — all role-specific dashboards, the shared component library, and the admin panel.

- Build the Candidate Dashboard: stats overview, applied jobs list, saved jobs grid, profile edit form

- Build the Employer Dashboard: stats overview, manage jobs table, job posting form, applications inbox

- Build the Admin Dashboard: user management table, content moderation, system statistics

- Build the shared UI component library: job cards, candidate cards, status badges, modals, alerts, pagination

- Build the Dashboard sidebar navigation with role-based menu items

- Build the profile picture and resume upload UI flows

- Build the rich-text job description editor in the employer job posting form

- Implement all in-app notification UI: notification bell, notification centre, read/unread states

- Implement client-side form validation across all dashboard forms

- Ensure all dashboard pages are fully mobile-responsive with collapsible sidebar

# 3. Week-by-Week Task Breakdown

Work is divided so backend and frontend can run in parallel from Week 3 onward. The first two weeks establish the shared foundation both sides depend on.

## Week 1 — Foundation

| Week | Backend Dev 1 (DB & API Core) | Backend Dev 2 (Auth & Services) | Frontend Dev 1 (Public Pages) | Frontend Dev 2 (Dashboards & UI) |
| --- | --- | --- | --- | --- |
| Week 1 | Set up solution structure, install NuGet packages, configure appsettings.json, write all EF Core entities and DbContext, create initial migration, seed database | Set up ASP.NET Identity, configure JWT settings, scaffold Auth controller, build register & login endpoints, implement password hashing | Set up Razor Pages project, install TailwindCSS, build _Layout, _Header, _Footer, _Navbar shared templates | Set up dashboard layout (_DashboardLayout), sidebar navigation skeleton, plan component library structure |

## Week 2 — Core Models & Auth

| Week | Backend Dev 1 (DB & API Core) | Backend Dev 2 (Auth & Services) | Frontend Dev 1 (Public Pages) | Frontend Dev 2 (Dashboards & UI) |
| --- | --- | --- | --- | --- |
| Week 2 | Build Repository base class and all entity repositories (Job, Application, SavedJob, SkillEvidence), write seed data for categories and skills | Complete auth flows: email verification, password reset, refresh tokens, RBAC policies; build UserProfileService | Build Home page (static sections, placeholder data), Login page, and Registration page with full client-side validation | Build Candidate Dashboard shell with stats overview cards (wired to mock data until API is ready) |

## Week 3 — API & Public Pages

| Week | Backend Dev 1 (DB & API Core) | Backend Dev 2 (Auth & Services) | Frontend Dev 1 (Public Pages) | Frontend Dev 2 (Dashboards & UI) |
| --- | --- | --- | --- | --- |
| Week 3 | Build all Opportunity endpoints (GET list with filters, GET detail, POST, PUT, DELETE, view tracking), add Swagger docs, write integration tests | Build ApplicationService and Application endpoints (apply, withdraw, status update), build SavedJobsService and endpoints | Build Opportunity Listing page with filter panel and search, build Opportunity Detail page with apply/save buttons | Connect Candidate Dashboard stats to live API, build Applied Jobs section with status filter |

## Week 4 — Profiles & Employer Features

| Week | Backend Dev 1 (DB & API Core) | Backend Dev 2 (Auth & Services) | Frontend Dev 1 (Public Pages) | Frontend Dev 2 (Dashboards & UI) |
| --- | --- | --- | --- | --- |
| Week 4 | Build Dashboard API endpoints (candidate stats, employer stats, admin stats), build Skills/Categories lookup endpoints | Build RecommendationService (skill-based matching), build employer dashboard API (manage jobs, applications inbox data) | Build Candidate Browse page, Candidate Profile Detail page, Employer Browse and Employer Detail pages | Build Employer Dashboard: manage jobs table (edit/close/delete actions), Job Posting form with full field set |

## Week 5 — Dashboards & Admin

| Week | Backend Dev 1 (DB & API Core) | Backend Dev 2 (Auth & Services) | Frontend Dev 1 (Public Pages) | Frontend Dev 2 (Dashboards & UI) |
| --- | --- | --- | --- | --- |
| Week 5 | Performance tuning: add DB indexes, fix N+1 queries, implement in-memory caching for category/skill lookups | Build Admin API endpoints (user management, content moderation, system stats), build Notification data model and service | Build Blog listing, Blog detail, Contact, and Pricing pages; complete mobile responsiveness audit for all public pages | Build Admin Dashboard (user table, moderation panel, stats); build shared component library (modals, pagination, alerts, badges) |

## Week 6 — Notifications, Search & Polish

| Week | Backend Dev 1 (DB & API Core) | Backend Dev 2 (Auth & Services) | Frontend Dev 1 (Public Pages) | Frontend Dev 2 (Dashboards & UI) |
| --- | --- | --- | --- | --- |
| Week 6 | Implement advanced search endpoint (multi-filter, relevance sorting), implement job alerts (Hangfire background job), write unit tests | Wire up SendGrid email templates for all notification types (welcome, application updates, deadline reminders, weekly recommendations) | Implement in-app notification bell and notification centre UI, connect recommendation API to candidate dashboard job feed | Build profile picture and resume upload flows, implement messaging UI, complete employer applications inbox with candidate preview modal |

## Week 7 — Testing, Hardening & Deployment

| Week | Backend Dev 1 (DB & API Core) | Backend Dev 2 (Auth & Services) | Frontend Dev 1 (Public Pages) | Frontend Dev 2 (Dashboards & UI) |
| --- | --- | --- | --- | --- |
| Week 7 | Security testing (SQL injection, XSS checks, auth bypass), finalize API docs, set up CI/CD pipeline (GitHub Actions), deploy to Azure | Integration tests for all service flows, load testing, error handling middleware review, configure Application Insights monitoring | Cross-browser testing, accessibility audit (WCAG), fix any responsive layout issues, final UX review of public pages | E2E flow testing (register → apply → dashboard), final dashboard QA, fix remaining UI bugs, prepare demo environment |

# 4. How the Team Works Together

## 4.1 Shared Contracts (API First)

BE1 and BE2 write and publish Swagger API docs before FE1/FE2 start wiring data. This means frontend developers can build with mock/stub data immediately and swap in real endpoints as they become available.

- BE1 publishes the Opportunities and Applications API contract by end of Week 2

- BE2 publishes the Auth and User Profile API contract by end of Week 2

- Both FE developers use Swagger UI to test endpoints independently

## 4.2 Git Branching Strategy

| main | Stable, deployable code only — merged after review |
| --- | --- |
| develop | Active integration branch — all features merge here first |
| feature/be1-* | BE1 feature branches (e.g. feature/be1-opportunities-api) |
| feature/be2-* | BE2 feature branches (e.g. feature/be2-auth-service) |
| feature/fe1-* | FE1 feature branches (e.g. feature/fe1-job-listing-page) |
| feature/fe2-* | FE2 feature branches (e.g. feature/fe2-employer-dashboard) |

## 4.3 Daily & Weekly Rhythm

- Daily 10-minute standup: What did you finish? What are you working on today? Any blockers?

- End of each week: each developer demos their completed work to the team

- BE1 and BE2 sync at least twice per week to coordinate shared database changes

- FE1 and FE2 sync at least twice per week to keep layouts and components consistent

- All four meet at the start of each new week to confirm priorities and dependencies

## 4.4 Dependency Management

Some frontend work depends on backend APIs being ready. The table below shows the key dependencies to watch:

| FE1 needs from BE1 | Opportunities list & detail endpoints (Week 3) |
| --- | --- |
| FE1 needs from BE2 | Auth endpoints — login/register (Week 2) |
| FE2 needs from BE1 | Dashboard stats endpoints (Week 4) |
| FE2 needs from BE2 | User profile endpoints, notification data (Week 4–5) |
| BE2 needs from BE1 | DbContext, entity models, and repositories (Week 1–2) |

## 4.5 Code Review Rules

- No one merges their own pull request — always get at least one review

- Backend PRs should be reviewed by the other backend developer

- Frontend PRs should be reviewed by the other frontend developer

- For any changes touching shared code (DbContext, layouts), all four review

# 5. Recommended Tools & Setup

| Version Control | Git + GitHub — one shared repository with the branching strategy above |
| --- | --- |
| Project Tracking | GitHub Projects (Kanban board) or Trello — one card per task, assigned by name |
| Communication | WhatsApp group for quick messages + weekly video call for demos |
| API Testing | Swagger UI (built into the project) + Postman for manual testing |
| IDE | Visual Studio 2022 (BE1, BE2) / VS Code (FE1, FE2) |
| Database | SQL Server Express (local) — BE1 manages the shared migrations |
| Design Reference | Figma or simple wireframes — FE2 maintains the shared component guide |
| Deployment | Azure App Service (free tier for dev/staging) — BE1 owns the pipeline |

# 6. Quick Reference — Who Owns What

| Backend Dev 1 | Backend Dev 2 | Frontend Dev 1 | Frontend Dev 2 |
| --- | --- | --- | --- |
| Database schema & migrations | Authentication & JWT | Shared layouts & navigation | Candidate dashboard |
| EF Core DbContext & repos | ASP.NET Identity & RBAC | Home & landing page | Employer dashboard |
| Opportunities API | User profile services | Job listing & search pages | Admin dashboard |
| Applications API | Recommendation engine | Job detail page | UI component library |
| Saved jobs API | Email notifications | Candidate profiles | In-app notifications UI |
| Skills & categories API | Dashboard stats API | Employer profiles | Upload flows & modals |
| DB indexes & caching | Background jobs (Hangfire) | Blog & contact pages | Mobile responsiveness |
| CI/CD & deployment | Monitoring & logging | Public page QA | E2E testing & demo env |

JobLink Hub Team Plan  |  Version 1.0